## ITREORG010 Risk Worksheet
Master Risks List - Contoso |  |  |  | Sources of Risk: People, Process, Technology, Environmental Factors | [7 empty] | List Last Reviewed: 4/3/2007
Project: IT Reorganization (ITREORG010) |  |  |  | Modes of Failure: Performance, Capability, Security, Cost
SOURCE OF RISK | DOWNSTREAM EFFECT | RISK CONDITION | EXPLANATION | OPERATIONAL CONSEQUENCES | BUSINESS EFFECT | PROBABILITY | INITIAL IMPACT | EXPOSURE | MITIGATION | CONTINGENCY | TRIGGER | LAST UPDATE | TEAM MEMBER ASSIGNED | ACTIONS | STATUS | MODIFIED PROBABILITY | MODIFIED IMPACT | EXPOSURE
Process | Performance Cost | Present service desk process inefficiencies could lead to increased cost to support current IT services. | Field office support is not a coordinated effort with centralized help desk functions. Often field support professionals respond to and resolve incidents without those incidents being recorded and a knowledge base being populated. | Without a comprehensive, shared knowledgebase of incidents, problems and resolutions, redundant incident and problem management activity will be performed throughout the support organization. | Extended service outages and inadequate communications regarding status of resolutions will further alienate the customer from IT. This will enforce the view of IT as not being aligned with the needs of the business. The perceived value of the services provided by IT will be diminished. | 70% | 5 | 3.5 | Implement MOF Incident and Problem management processes. Coordinate second and third line support groups. | Allocation of excessive resources to accommodate firefighting reactive issues. Bear the costs of increased support activities and staff. | Continual firefighting. Repeated problems occur. Uncoordinated and recurring changes. Poor meantime to resolution. |  | Team A | Probability has decreased due to the implementations of MOF-based incident and problem management processes. Original probability will be kept in the Master Risk List and Risk Knowledge Base for historical purposes. | Open | 40% | 5 | 2
People | Performance Capability | Changes implemented by one IT group could negatively affect systems and services delivered to other IT groups. | Although change management exists within some groups, a common formal change management process does not exist across all IT groups. Additionally, some changes, when reviewed at the weekly status meeting, have not been properly assessed for impact to all groups. | Lack of commitment to a standard set of operational processes will lead to business units that fail to trust each other. Frustration between IT groups will occur as systems under the responsibility of one group will be affected by others. | Service disruptions caused by failed changes will interrupt business functions. Additionally, failure to communicate planned downtime of mission-critical services to users and the help desk before service interruptions occur will result in reduced trust in IT. This lack of trust will force the business to wonder about the value of the current IT operations and force them to think about outsourcing IT functions. | 65% | 5 | 3.25 | A standard formalized and communicated MOF-based change management process will be implemented across all IT groups. | Assign additional resources to reactive problem management. Communication to customers and end-users in a prompt, descriptive, and meaningful manner can reduce the negative effect on customer satisfaction. | Information gathered during project status meetings and operations management reviews regarding process and service outages indicate that this risk is currently being actualized at some level. |  | Team B | Probability has decreased due to the implementation of MOF-based change management processes. Original probability will be kept in the master risks list and risk knowledge base for historical purposes. | Open | 35% | 5 | 1.75
Note on A6: Source of Risk: People. Everyone makes mistakes—either due to lack of experience or due to lack of time. So even if a group’s processes and technology are flawless, these human errors can put the business at risk. Process. Flawed or badly documented processes can put the business at risk even if they are followed perfectly. Technology. The IT staff may perfectly follow a well-designed process, yet fail the business because of problems with the hardware, software, and so on. External. Some factors are beyond the IT group’s control but can still harm the infrastructure in a way that fails the business. Natural events such as earthquakes and floods fall into this category, as do externally generated, man-made problems such as civil unrest, computer virus attacks, and changes to government regulations.
Note on B6: Downstream Effect: Performance. The infrastructure can fail to meet users’ expectations (in reliability, for example), either because the expectations were set wrong, or because the hardware or software performs incorrectly. Security. The infrastructure can fail the business by not providing enough protection for data and resources, or by enforcing so much security that legitimate users can’t access data and resources. Capability. The infrastructure can work properly, but be unable to change quickly enough to meet the business needs. Capacity problems are the most obvious case. In addition, agility can often be related to complexity. For example, if a solution is too complex to change and then manage, capability is compromised. Cost. The infrastructure can work properly, but at too high a cost, causing too little return on investment.
Note on C6: Condition: The “if” part of an if-then statement. (The “then” part is the consequence.) For example, look at the following sentence: If the Web server’s sole power supply fails, then the company’s Web site will be unavailable. The condition is “If the Web server’s sole power supply fails” and the consequence is “the company’s Web site will be unavailable.”
Note on D6: Explanation: Detail on the Risk Condition
Note on E6: Operational Consequence: A description of the way in which the condition would affect the IT environment. The mode of failure typically influences the operational consequence.
Note on F6: Business Effect: In the MOF risk model, a description of the way in which the operational consequence would affect the business as a whole.
Note on G6: Probability: The likelihood that the condition will actually occur, expressed in percentage. Risk probability must be greater than 0 percent and less than 100 percent. (If the probability is zero, the risk does not pose a threat to the business; if the probability is 100, the risk is a certainty, and is a known problem.)
Note on H6: Impact: Risk impact measures the severity of adverse effects, or the magnitude of a loss, caused by the consequences. The most effective solution is a numeric scale. Scale is 1 - 5
Note on I6: Exposure: The exposure is the result of multiplying the probability by the impact. Sometimes a high-probability risk has low impact and can be safely ignored; likewise, a high-impact risk sometimes has low probability and can be safely ignored. The risks that have high probability and high impact are the ones most worth managing, and they’re the ones that produce the highest exposure values.
Note on J6: Mitigations: Mitigations are steps the team can take before the condition occurs, and each has one of three effects on the risk: • Reduce: Risk reduction minimizes the risk’s probability or its impact, or both. Ideally, a reduction method reduces probability or impact to zero, but this is not always possible. • Avoid: Risk avoidance prevents the team from taking actions that increase exposure too much to justify the benefit. • Transfer: Whereas the avoidance strategy eliminates a risk, the transference strategy often leaves the risk intact but shifts responsibility for it to another group to reduce the risk.
Note on K6: Contingencies: A contingency is a step the team takes if the condition occurs or a trigger becomes true. The contingency plan documents the set of contingencies the team will use when reacting to a particular condition.
Note on L6: Triggers: Triggers are indicators that tell the team a condition is about to occur, or has occurred, and therefore it is time to put the contingency plan into effect. Ideally, the trigger becomes true before the consequences occur. It may help to think of triggers as warning lights that illuminate while there is still time to avoid danger.
Note on P6: Status: Open: Risk is still a risk Closed: Risk probability hits 100% or reduces to 0

## ITMOM001 Risk Worksheet
Master Risks List - Contoso |  |  |  | Sources of Risk: People, Process, Technology, Environmental Factors | [7 empty] | List Last Reviewed: 4/3/2003
Project: IT Operations Manager (ITMOM001) |  |  |  | Modes of Failure: Performance, Capability, Security, Cost
SOURCE OF RISK | DOWNSTREAM EFFECT | RISK CONDITION | EXPLANATION | OPERATIONAL CONSEQUENCES | BUSINESS EFFECT | PROBABILITY | INITIAL IMPACT | EXPOSURE | MITIGATION | CONTINGENCY | TRIGGER | LAST UPDATE | TEAM MEMBER ASSIGNED | ACTIONS | STATUS | MODIFIED PROBABILITY | MODIFIED IMPACT | EXPOSURE
Technology | Cost Capability Performance | Test environment may not be available for testing prior to implementation | Hardware has been ordered for the test environment; but even with equipment available, the proper application environment (that is, Active Directory® and Microsoft® Exchange Server) may not be available or configured as it is in production. | Proper testing of monitoring specific applications in a lab environment may not be available. Unknown performance and security incidents could occur during production deployment. Architecture and design specifications cannot be validated or modified prior to production deployment. | Service outages could occur to mission-critical services. This would have a negative and unknown impact on business revenue. The perceived value of the services provided by IT will be diminished. | 80% | 5 | 4 | Establish an additional external vendor relationship for temporary or permanent hardware acquisition suitable for lab environment. Utilize virtual machines within available hardware to simulate additional hardware. | Examine cost of delay to production implementation. Borrow equipment currently being utilized for other lower priority purpose. Notify operations staff of significant change procedure to copy production environment to test environment. | Frequent monitoring of requisition process shows no progress to hardware arrival. |  | Team A | Probability has decreased due to new relationship with Vendor X. This will allow the rapid acquisition of necessary hardware, if needed. Original probability will be kept in the master risks list and risk knowledge base for historical purposes. | Open | 30% | 5 | 1.5
People | Capability Cost | Project team personnel changes could affect release schedule | Changes to personnel requirements or actual job changes. | Project schedule and release date is pushed back to an unknown time. | Could affect delivered functionality of monitoring solution in order to meet availability windows. | 20% | 5 | 1 | Maintain regular communication with all project managers and project sponsors. | Aggressively train and go through knowledge transfer. Adjust deployment schedule as necessary. | Personnel involved with project turnover or Contoso financial situation greatly changes. |  | Team B | Probability has increased due to project team member changes. Original probability will be kept in the master risks list and risk knowledge base for historical purposes. | Open | 70% | 5 | 3.5
Note on A6: Source of Risk: People. Everyone makes mistakes—either due to lack of experience or due to lack of time. So even if a group’s processes and technology are flawless, these human errors can put the business at risk. Process. Flawed or badly documented processes can put the business at risk even if they are followed perfectly. Technology. The IT staff may perfectly follow a well-designed process, yet fail the business because of problems with the hardware, software, and so on. External. Some factors are beyond the IT group’s control but can still harm the infrastructure in a way that fails the business. Natural events such as earthquakes and floods fall into this category, as do externally generated, man-made problems such as civil unrest, computer virus attacks, and changes to government regulations.
Note on B6: Downstream Effect: Performance. The infrastructure can fail to meet users’ expectations (in reliability, for example), either because the expectations were set wrong, or because the hardware or software performs incorrectly. Security. The infrastructure can fail the business by not providing enough protection for data and resources, or by enforcing so much security that legitimate users can’t access data and resources. Capability. The infrastructure can work properly, but be unable to change quickly enough to meet the business needs. Capacity problems are the most obvious case. In addition, agility can often be related to complexity. For example, if a solution is too complex to change and then manage, capability is compromised. Cost. The infrastructure can work properly, but at too high a cost, causing too little return on investment.
Note on C6: Condition: The “if” part of an if-then statement. (The “then” part is the consequence.) For example, look at the following sentence: If the Web server’s sole power supply fails, then the company’s Web site will be unavailable. The condition is “If the Web server’s sole power supply fails” and the consequence is “the company’s Web site will be unavailable.”
Note on D6: Explanation: Detail on the Risk Condition
Note on E6: Operational Consequence: A description of the way in which the condition would affect the IT environment. The mode of failure typically influences the operational consequence.
Note on F6: Business Effect: In the MOF risk model, a description of the way in which the operational consequence would affect the business as a whole.
Note on G6: Probability: The likelihood that the condition will actually occur, expressed in percentage. Risk probability must be greater than 0 percent and less than 100 percent. (If the probability is zero, the risk does not pose a threat to the business; if the probability is 100, the risk is a certainty, and is a known problem.)
Note on H6: Impact: Risk impact measures the severity of adverse effects, or the magnitude of a loss, caused by the consequences. The most effective solution is a numeric scale. Scale is 1 - 5
Note on I6: Exposure: The exposure is the result of multiplying the probability by the impact. Sometimes a high-probability risk has low impact and can be safely ignored; likewise, a high-impact risk sometimes has low probability and can be safely ignored. The risks that have high probability and high impact are the ones most worth managing, and they’re the ones that produce the highest exposure values.
Note on J6: Mitigations: Mitigations are steps the team can take before the condition occurs, and each has one of three effects on the risk: • Reduce: Risk reduction minimizes the risk’s probability or its impact, or both. Ideally, a reduction method reduces probability or impact to zero, but this is not always possible. • Avoid: Risk avoidance prevents the team from taking actions that increase exposure too much to justify the benefit. • Transfer: Whereas the avoidance strategy eliminates a risk, the transference strategy often leaves the risk intact but shifts responsibility for it to another group to reduce the risk.
Note on K6: Contingencies: A contingency is a step the team takes if the condition occurs or a trigger becomes true. The contingency plan documents the set of contingencies the team will use when reacting to a particular condition.
Note on L6: Triggers: Triggers are indicators that tell the team a condition is about to occur, or has occurred, and therefore it is time to put the contingency plan into effect. Ideally, the trigger becomes true before the consequences occur. It may help to think of triggers as warning lights that illuminate while there is still time to avoid danger.
Note on P6: Status: Open: Risk is still a risk Closed: Risk probability hits 100% or reduces to 0