## Blad1
Item Identifier	Current Version	Item Title	Date of last status change	Date of last review	Person who reviewed	Owner	Location	Copy Holders	Item type	Item attributes	Stage	Users	Producer	Date allocated	Relationship with other items
CIT	1	CI Table	11-9-2017			Sjoerd Brauer	40configuration_management\configuration _item_table		Document	ODS file	Under review	Group	Sjoerd Brauer	11-9-2017	CMP
PP	1	Project Plan	11-9-2017	11-9-2017	Loek Ehren	Nils Nieuwenhuis	10projectplan\projectPlanDraft		Document	PDF file	In development	Group	Nils Nieuwenhuis	8-9-2017
US	4.1	User stories	12-9-2017	12-9-2017	Loek Ehren	Sjoerd Brauer	30analysis\User stories		Document	PDF file	Finished	Group	Sjoerd Brauer	8-9-2017	USD
DM	2	Domain model	8-9-2017	8-9-2017	Tobias Derksen	Sjoerd Brauer	30analysis		Document	UXF file	Finished	Group	Sjoerd Brauer	7-9-2017
CMP	1	Configuration Management plan	11-9-2017	12-9-2017	Nils Nieuwenhuis	Sjoerd Brauer	40configuration_management\plan		Document	PDF file	Finished	Group	Sjoerd Brauer	11-9-2017	CIT
QMP	1	Quality Management plan	11-9-2017	18-9-2017	Sjoerd Brauer	Loek Ehren	20qualityplan\quality_standards\		Document	PDF file	In development	Group	Loek Ehren	11-9-2017
SRS	1	Software Requirements Specification	11-9-2017			Loek Ehren	20requirements		Document	PDF file	In development	Group	Loek Ehren	11-9-2017
USD	1	User stories diagram	14-9-2017			Sjoerd Brauer	30analysis\User stories		Document	UXF file	under review	Group	Sjoerd Brauer	14-9-2017	US
JBFR	1	Java backend framework research	21-9-2017			Sjoerd Brauer	30analysis\java_frameworks_backend		Document	PDF file	under review	Customer	Sjoerd Brauer	19-9-2017	JBP
JBP	1	Java backend proposal	23-9-2017			Sjoerd Brauer	35proposals\java_backend_proposal		Document	PDF file	under review	Customer	Sjoerd Brauer	19-9-2017	JBFR
BA	2	Backend architecture	19-12-2017	19-12-2017	Group	Sjoerd Brauer	40configuration_management\configuration_item_table		Document	PDF file	finished	Group	Sjoerd Brauer	25-9-2017
M	5	Mockups	19-12-2017	19-12-2017	Group	Sjoerd Brauer	70design\mockups		Document	PDF file	finished	Group	Sjoerd Brauer	25-9-2017
DB-DOC	2	Database Documentation	15-01-2018			Tobias Derksen	50database		Document	PDF file	finished	Group	Tobias Derksen	24-10-2017
BAE	1	Backend architecture aesthetic	1-8-2018			Sjoerd Brauer	100documentation		Document	PDF file	finished	Next group	Sjoerd Brauer	1-8-2018
FEDD	1	Frontend diagrams	1-8-2018			Sjoerd Brauer	100documentation\frontend		Documents	UXF file	finished	Next group	Sjoerd Brauer	1-8-2018
PR	1	PDF research	21-12-2017		Group	Sjoerd Brauer	30analysis\pdfgeneration		Document	PDF file	finished	Customer	Sjoerd Brauer	14-12-2017